## Endpoints
API Endpoints | FastAPI REST + WebSocket events — PX4_DXP Rover Server
Group | Method | Route | Auth Required | Description
System | GET | /api/ping | No | Liveness probe — returns {status, timestamp}
System | GET | /api/healthz | No | Readiness check: ROS connectivity, FCU link, RPP state, pose freshness
System | GET | /api/health/bridge | No | MAVROS bridge liveness + recovery state (Phase 3A observe-only watchdog)
System | GET | /api/activity | No | Activity log (info/warning/error) — last 500 entries as bounded deque
System | POST | /api/discover | No | UDP beacon discovery — returns list of rovers broadcasting on LAN
Vehicle | POST | /api/arm | Yes | Arm or disarm the vehicle asynchronously; returns {success, message}
Vehicle | POST | /api/set_mode | Yes | Set FCU mode (MANUAL ¦ OFFBOARD); uses call_async + done_callback
Vehicle | POST | /api/estop | Yes | Emergency stop — publishes current pos as single-point path; RPP ignores empty Path
Telemetry | GET | /api/telemetry/latest | No | Snapshot of all telemetry fields: pos, heading, xtrack, RPP state, armed, battery, GPS, marking_state
Mission | POST | /api/mission/load | Yes | Load path by name or mission_file; returns loaded path name + waypoint count
Mission | POST | /api/mission/start | Yes | Arm → OFFBOARD → publish path; optionally auto-origin from rover pose
Mission | POST | /api/mission/stop | Yes | Publish stop-path (stay armed, no disarm)
Mission | POST | /api/mission/abort | Yes | Hard abort: stop-path + MANUAL + disarm
Mission | GET | /api/mission/status | Yes | Current state + RPP snapshot: dist_to_goal, speed, xtrack, pose_age_ms, fcu_connected
Paths | GET | /api/paths | Yes | List all built-in + uploaded paths with summaries
Paths | GET | /api/path/{name}/preview | Yes | Return local-NED waypoints + bounds for display (DXF planning offloaded to thread)
Paths | GET | /api/path/{name}/entities | Yes | Per-entity DXF preview geometry (LINE/CIRCLE/ARC/LWPOLYLINE) without full planning
Paths | POST | /api/path/{name}/entities | Yes | Save per-entity spray ON/OFF overrides for a DXF path
Paths | GET | /api/path/{name}/extensions | Yes | Return saved PRE/AFT extension config for a DXF file
Paths | POST | /api/path/{name}/extensions | Yes | Save DXF extension config (pre/aft spray lead-in/out metres)
Paths | POST | /api/path/upload | Yes | Upload .waypoints/.csv/.dxf — returns saved filename + size
Paths | POST | /api/path/publish | Yes | Publish named path to /path ROS2 topic
Paths | POST | /api/path/parse-dxf | Yes | Parse uploaded DXF; return entity list + layer names (no persist until success)
Paths | POST | /api/path/plan | Yes | Run full planning pipeline (coverage, arc discretization, spray compensation) → merged waypoints + spray flags + mission_id
Paths | POST | /api/path/load-to-controller | Yes | Load staged+aligned mission to OffboardController (reads JSON artifact, commits to controller)
Paths | DELETE | /api/path/{filename} | Yes | Delete an uploaded file by filename
RPP Params | GET | /api/rpp/params | Yes | List all RPP params with schema + live values (offline: schema only)
RPP Params | GET | /api/rpp/params/schema | Yes | Param metadata only (type, default, group, description, bounds) — no ROS calls
RPP Params | GET | /api/rpp/params/{name} | Yes | Get a single RPP param value from the running node
RPP Params | PUT | /api/rpp/params/{name} | Yes | Set a single RPP param at runtime — no node restart required
RPP Params | PUT | /api/rpp/params | Yes | Bulk-set multiple RPP params atomically
PX4 Params | GET | /api/params/{name} | Yes | Get a single PX4 parameter via MAVROS bridge
PX4 Params | POST | /api/params/{name} | Yes | Set a single PX4 parameter value (QGC is source of truth — use with care)
Spray | POST | /api/spray/test | Yes | Manual spray ON with timed auto-off (max 10s, default 3s) or immediate OFF
Spray | GET | /api/spray/status | Yes | Actual vs desired vs manual-override spray state
RTK | POST | /api/rtk/ntrip/start | Yes | Start NTRIP correction stream (host, port, mountpoint, user, password)
RTK | POST | /api/rtk/lora/start | Yes | Start LoRa RTK (baudrate, serial_port)
RTK | POST | /api/rtk/stop | Yes | Stop all active RTK streams
RTK | GET | /api/rtk/status | Yes | RTK stream status: mode, pid, running, healthy, frames/bytes, last_frame_age_s
WebSocket | PUSH | telemetry | N/A | 10 Hz push: pos, heading, xtrack, speed, RPP state, armed, battery, GPS, marking_state
WebSocket | PUSH | mission_status | N/A | Push on any state change: state + RPP snapshot
WebSocket | PUSH | mission_completed | N/A | Triggered on DONE settle — mission finished normally
WebSocket | PUSH | safety_abort | N/A | Fired when stale/disconnected watchdog triggers; includes reason + state
WebSocket | PUSH | rover_disconnected | N/A | Emitted when FCU connection is lost during a mission

## ROS2 Nodes
ROS2 Nodes | Active and external nodes in the rpp-pipeline stack
Node Name | Source File | Category | Description | Subscribes To | Publishes | Key Params
rpp_controller_node | src/rpp_controller_node.py | Core | Regulated Pure Pursuit path tracker with predictive curvature (P1.1), adaptive lookahead (P1.2), corner smoothing (P1.3), lateral-accel constraint (P4.1), and feedforward yaw rate (P3.1). Publishes NED velocity and spray active flag. | /path, /mavros/local_position/pose, /mavros/gpsstatus/gps1/raw | /rpp/velocity_ned, /rpp/debug, /rpp/yaw_rate_body (opt), /spray/active | 36+ live-tunable (see Params sheet)
mission_runner_node | src/mission_runner_node.py | Core | OFFBOARD orchestration: waits for FCU connection, confirms setpoint stream, switches to OFFBOARD, arms, monitors DONE settle, disarms, returns to MANUAL. | /rpp/debug (state code), /mavros/state | Service calls only (arm, set_mode) | mission_timeout_s, done_settle_s
path_publisher_node | src/path_publisher_node.py | Core | Emits hardcoded test paths (straight_5m, arc_quarter_1m5, lshape_2x2, square_2x2, rectangle_3x2, circle_1m5) or loads QGC .waypoints/.csv for SITL/hardware bring-up. | — | /path (nav_msgs/Path, LOCAL_NED) | path_name, mission_file
twist_to_setpoint_node | src/twist_to_setpoint_node.py | Core | Converts NED velocity + optional yaw_rate into MAVROS PositionTarget at 50 Hz with stale-input handling. Acts as the continuous OFFBOARD heartbeat — never gaps. | /rpp/velocity_ned, /rpp/yaw_rate_body (opt) | /mavros/setpoint_raw/local (PositionTarget, 50 Hz) | input_max_age_s
spray_controller_node | src/spray_controller_node.py | Phase 3 | Edge-detects spray state changes (MARK ↔ TRANSIT), debounces for 3 samples (≈60ms), fires MAVLink DO_SET_ACTUATOR (cmd 187), re-asserts at 2 Hz, and forces OFF on disarm/non-OFFBOARD/staleness/shutdown. | /spray/active (desired), /mavros/state | /spray/state (actual), /spray/manual_state | actuator_set_index, on_value, off_value, debounce_samples, reassert_hz, active_timeout_s
xtrack_logger_node | src/xtrack_logger_node.py | Debug | Subscribes to /rpp/debug, extracts cross-track error and curvature per tick, writes timestamped CSV for post-flight analysis. | /rpp/debug (Float32MultiArray) | CSV file on disk | log_file, frame_id
ntrip_rtcm_node | ntrip_rtcm_node.py | External RTK | Connects to an NTRIP caster via credentials from ntrip.env, streams RTCM3 correction data to /mavros/rtcm for the FCU EKF. | NTRIP caster (internet) | /mavros/rtcm (RTCM corrections) | Host, port, mountpoint, user, pass (env-based)
lora_rtcm_node | lora_rtcm_node.py | External RTK | Reads RTCM3 corrections from a LoRa radio on a serial port and forwards them to /mavros/rtcm for RTK fix. | Serial port (LoRa radio) | /mavros/rtcm (RTCM corrections) | baudrate, serial_port

## Files
File Inventory | All significant source, config, and doc files with one-line descriptions
Area | File Path | Type | Description
ROS2 Nodes | src/rpp_controller_node.py | Python | Regulated Pure Pursuit controller — core tracking, curvature, spray flag output (117 KB)
ROS2 Nodes | src/mission_runner_node.py | Python | OFFBOARD orchestration: arm, switch mode, monitor mission lifecycle (27 KB)
ROS2 Nodes | src/path_publisher_node.py | Python | Hardcoded test paths + QGC .waypoints/.csv loader for bring-up (23 KB)
ROS2 Nodes | src/twist_to_setpoint_node.py | Python | NED velocity → OFFBOARD PositionTarget heartbeat at 50 Hz (14 KB)
ROS2 Nodes | src/spray_controller_node.py | Python | Servo/solenoid edge-detect + MAVLink DO_SET_ACTUATOR safety controller (14 KB)
ROS2 Nodes | src/xtrack_logger_node.py | Python | Debug CSV logger: xtrack + curvature from /rpp/debug (11 KB)
ROS2 Nodes | src/launch/rpp_pipeline.launch.py | Python | ROS2 launch file for the full RPP pipeline stack
Server | server/main.py | Python | FastAPI app factory, lifespan (startup/shutdown), 10 Hz telemetry loop, safety watchdog
Server | server/ros_node.py | Python | ROS2 bridge: subscribers (pose, state, battery, GPS, RPP debug), publishers, service clients
Server | server/offboard_controller.py | Python | Mission state machine: IDLE→LOADING→ARMING→OFFBOARD→RUNNING→STOPPING→DISARMING→COMPLETED/ABORTED
Server | server/path_manager.py | Python | Path load/list/preview/delete, DXF entity parse + overrides, extension config, staging
Server | server/mission_loading.py | Python | Async path load, auto-origin from MAVROS pose, spray_flags_for_path helper
Server | server/emergency.py | Python | E-stop: publishes single-point path to halt rover, optional disarm
Server | server/rtk_manager.py | Python | Async NTRIP/LoRa subprocess management: start/stop/status/health
Server | server/bridge_health.py | Python | Phase 3 MAVROS watchdog: detect frozen /mavros/state, auto-recover (observe-only default)
Server | server/beacon.py | Python | UDP discovery: broadcast rover identity on LAN, cache peer rovers
Server | server/auth.py | Python | Bearer token auth: load or create ~/.rover_token, env var override ROVER_DISABLE_AUTH
Server | server/config.py | Python | Central constants: topic/service names, RPP state codes, thresholds, spray defaults
Server | server/models.py | Python | Pydantic models: ArmRequest, ModeRequest, TelemetryData, RppParamInfo, PathPlanResponse, …
Server Routes | server/routes/system.py | Python | Handlers for /ping, /healthz, /health/bridge, /activity, /discover
Server Routes | server/routes/vehicle.py | Python | Handlers for /arm, /set_mode, /estop
Server Routes | server/routes/mission.py | Python | Handlers for /mission/load, start, stop, abort, status
Server Routes | server/routes/path.py | Python | Handlers for path list, preview, entities, extensions, upload, publish, parse-dxf, plan, load-to-controller, delete
Server Routes | server/routes/rpp_params.py | Python | Handlers for /rpp/params list+schema+get+put (single and bulk)
Server Routes | server/routes/params.py | Python | Handlers for /params/{name} get/set PX4 params via MAVROS
Server Routes | server/routes/spray.py | Python | Handlers for /spray/test and /spray/status
Server Routes | server/routes/rtk.py | Python | Handlers for RTK start (NTRIP/LoRa), stop, status
Server Routes | server/routes/telemetry.py | Python | Handler for /telemetry/latest (no auth)
Server Sockets | server/sockets/events.py | Python | register_handlers(sio) — wires telemetry/mission_status/mission_completed/safety_abort/rover_disconnected
Path Engine | path_engine/core.py | Python | Data models: PlannedPath, PathSegment, SegmentType (MARK/TRANSIT), DXFEntity, spray_flags
Path Engine | path_engine/engine.py | Python | Top-level planning orchestration — calls all sub-planners in order
Path Engine | path_engine/spray.py | Python | Spray latency compensation: spatial lead-in/out point insertion
Path Engine | path_engine/parser/dxf_parser.py | Python | ezdxf-based DXF parser: LINE, POINT, CIRCLE, ARC, LWPOLYLINE (bulge), SPLINE, ELLIPSE
Path Engine | path_engine/ned.py | Python | NED coordinate transform utilities
Path Engine | path_engine/validator.py | Python | Path validation: closure checks, geometry bounds, RMSE quality gate
Path Engine | path_engine/cli.py | Python | CLI entry point for offline path planning
Config | config/ntrip.env | Env | NTRIP credentials (gitignored) — host, port, mountpoint, user, password
Config | config/robot_localization.yaml | YAML | EKF fusion config for robot_localization (Phase 4 — not yet deployed)
Config | px4_pluginlists_rover.yaml | YAML | MAVROS plugin allowlist: deny actuator_control, allow command plugin
Scripts | px4_start_service.sh | Shell | systemd ExecStart for px4-dxp service — starts MAVROS + NTRIP + all nodes
Scripts | rpp_start.sh | Shell | systemd ExecStart for rpp-pipeline — source ROS2, launch RPP nodes
Scripts | deploy.sh | Shell | Full deploy: git pull + daemon-reload + all service restarts
Scripts | tools/capture_telemetry.py | Python | WebSocket sniff tool: NDJSON output, -n samples, --host override
Service Units | px4-dxp.service | Systemd | Umbrella service: MAVROS + NTRIP + QGC bridge (restart cascades to rpp-pipeline)
Service Units | rover-server.service | Systemd | FastAPI server (port 5001) — restart on any server/** change
Service Units | rpp-pipeline.service | Systemd | RPP node pipeline — PartOf=px4-dxp; restart on any src/*.py change
Docs | docs/SPRAY_SERVO_INTEGRATION.md | Markdown | Phase 3 integration spec: wiring, firmware config, software architecture, safety checklist
Docs | docs/MAVROS_BRIDGE_INVENTORY.md | Markdown | MAVROS plugin allowlist + service mapping reference
Docs | docs/superpowers/plans/2026-06-02-corner-xtrack-reduction.md | Markdown | Sprint plan for corner xtrack ≤5cm: param sweep, a_lat_max tuning, validation tasks
Docs | docs/superpowers/plans/2026-06-10-spray-servo-integration.md | Markdown | Full Phase 3 spray build plan + safety checklist (servo → MAVLink → flag propagation → latency)
Root | CLAUDE.md | Markdown | Runtime context for AI agents: hardware, GCS info, critical rules, quick reference
Root | INTEGRATION_ARCHITECTURE.md | Markdown | End-to-end system diagram: GCS ↔ Jetson ↔ PX4 ↔ sensors
Root | ntrip_rtcm_node.py | Python | NTRIP client subprocess: streams RTCM3 to /mavros/rtcm
Root | lora_rtcm_node.py | Python | LoRa RTK client: reads serial RTCM3 corrections, forwards to /mavros/rtcm

## Features
Features & Capabilities | All implemented and planned system capabilities
Phase | Category | Feature | Status | Description
Phase 2 | Navigation | Regulated Pure Pursuit | Live | Core path tracking: geometric lookahead + curvature-based steering for ground rover
Phase 2 | Navigation | Predictive Curvature (P1.1) | Live | Worst-κ lookahead over next N points prevents centrifugal overshoot on curves
Phase 2 | Navigation | Adaptive Lookahead (P1.2) | Live | L_d grows with cross-track error (xtrack_lookahead_gain) to correct large deviations faster
Phase 2 | Navigation | Path Conditioning (P1.3) | Live | Corner smoothing arcs (r=0.5m) + uniform linear resampling (0.08m) before tracking
Phase 2 | Navigation | Lateral Accel Constraint (P4.1) | Live | v ≤ sqrt(a_lat_max / ¦κ¦) on curves — prevents wheel spin and side-slip
Phase 2 | Navigation | Feedforward Yaw Rate (P3.1) | Live | ω = κ·v + k_ψ·θ_e — curvature feedforward + heading-error feedback on yaw
Phase 2 | Navigation | Pose Extrapolation (P2.4) | Live (opt) | Velocity-based latency closure: projects pose forward by comms lag before control
Phase 2 | Safety | EKF/RTK Jump Detection (P0.2) | Live | Skips position spikes > ekf_jump_threshold_m to reject GPS multipath corruptions
Phase 2 | Safety | RTK Fix Gating (P0.3) | Live | Refuses non-zero velocity output unless MAVROS reports fix_type=6 (RTK Fixed)
Phase 2 | Safety | OFFBOARD Heartbeat | Live | twist_to_setpoint publishes PositionTarget at 50 Hz continuously — never gaps, fail-safe zero-vel on stale input
Phase 2 | Safety | Pose Staleness Watchdog | Live | RPP halts if local_position/pose older than pose_max_age_s (default 0.5s)
Phase 2 | Safety | MAVROS Crash Detection | Live | Server overrides TRANSIENT_LOCAL stale connected=True after 2s via _state_recv_time
Phase 2 | Navigation | Tracking Profiles | Live | tracking_profile=auto¦segment¦smooth — auto splits missions per entity type: lines→segment (stop-and-pivot corners), arcs/circles→smooth RPP
Phase 2 | Navigation | Segment Profile | Live | Stop-and-pivot at hard corners: slowdown zone, heading align gate, then advance — precise right-angle turns — FIELD VALIDATED 2026-06-12 (square_cornerfix): 0.52cm RMS / 2.17cm max, corner ≤5cm goal MET.
Phase 2 | Navigation | Smooth Profile | Live | Pure continuous RPP for arc/circle entities — no pivot stops, smooth curvature-based steering — at structural floor ~2-3cm (ω/RO_YAW_P heading lag); DEFERRED, not on critical path.
Phase 2 | Mission | E-Stop | Live | POST /api/estop publishes current pos as single-point path — RPP converges and halts in place
Phase 2 | Mission | Mission State Machine | Live | IDLE→LOADING→ARMING→SWITCHING_OFFBOARD→RUNNING→STOPPING→DISARMING→COMPLETED/ABORTED
Phase 2 | Mission | Async Arm/Mode | Live | arm_async(), set_mode_async() use call_async + add_done_callback — non-blocking
Phase 3 | Spray | Spray Flag Transport | Live | spray_flags carried per-point via Path z-channel (pose.position.z = 1.0/0.0)
Phase 3 | Spray | Spray State Machine | Live | rpp_controller decides MARK vs TRANSIT per segment, publishes /spray/active Bool
Phase 3 | Spray | Spray Controller Node | Live | Edge-detect → debounce (3 samples) → DO_SET_ACTUATOR (cmd 187) → re-assert 2Hz
Phase 3 | Spray | Spray Latency Compensation | Live | path_engine.spray inserts spatial lead-in/out points to compensate solenoid ON/OFF delay
Phase 3 | Spray | Manual Spray Test | Live | POST /api/spray/test: timed ON with auto-off (max 10s) for bench verification
Phase 3 | Spray | Marking Status Telemetry | Live | marking_state: off/transit/marking pushed via WebSocket at 10 Hz to frontend
Phase 3 | Safety | Spray Fail-Safes | Live | Force OFF on: disarm, non-OFFBOARD, /spray/active staleness (>0.5s), shutdown, E-stop
Phase 2 | Planning | DXF Import | Live | ezdxf parser: LINE, CIRCLE, ARC, LWPOLYLINE (with bulge), SPLINE, ELLIPSE, POINT
Phase 2 | Planning | Arc Discretization | Live | Chord-error/sagitta method with configurable density for smooth arc → waypoint conversion
Phase 2 | Planning | Segment Ordering (TSP) | Live | Nearest-neighbour TSP + endpoint reversal minimises dead-travel between DXF entities
Phase 2 | Planning | Transit Insertion | Live | Automatic TRANSIT segments (0.5m/s) between MARK segments for rover repositioning
Phase 2 | Planning | QGC .waypoints Support | Live | Geographiclib Karney geodesic converts lat/lon to local NED for mission replay
Phase 2 | Planning | CSV Mission Support | Live | 2-col (N,E metres) and 6-col (+ spray flags + velocity profile) CSV formats
Phase 2 | Planning | DXF→NED Alignment | Live | Least-squares alignment via reference points with RMSE quality gate (≤0.05m)
Phase 2 | Planning | Mission Staging + Preview | Live | Aligned missions staged to JSON; operator reviews in frontend before committing to controller
Phase 2 | Planning | Per-Entity Spray Overrides | Live | UI toggle mark/no-mark per DXF entity; stored and respected during planning
Phase 2 | Planning | Extension Config | Live | Pre/aft lead-in/out per DXF file (metres); configurable via /api/path/{name}/extensions
Phase 2 | Server | Token Auth | Live | Bearer token stored in ~/.rover_token; env override ROVER_DISABLE_AUTH for dev
Phase 2 | Server | GZip Compression | Live | Responses >1KB automatically gzip-compressed
Phase 2 | Server | WebSocket Telemetry | Live | Socket.IO 10Hz push: telemetry, mission_status, mission_completed, safety_abort, rover_disconnected
Phase 2 | Server | UDP Beacon Discovery | Live | Rover broadcasts rover_id + server_port on LAN; listeners cache peer rovers
Phase 2 | Server | Activity Log | Live | Bounded deque (500 entries): info/warning/error events with timestamp
Phase 2 | Server | Systemd Watchdog | Live | sdnotify heartbeat every ~3s for WatchdogSec in px4-dxp.service
Phase 2 | RTK | NTRIP Client | Live | Async subprocess: connects to caster, streams RTCM3 to /mavros/rtcm
Phase 2 | RTK | LoRa RTK | Live | Async subprocess: reads serial RTCM3 corrections, forwards to /mavros/rtcm
Phase 2 | RTK | RTK Status API | Live | Reports mode, pid, healthy, frames/bytes, last_frame_age_s
Phase 4 | Sensor Fusion | robot_localization Fusion | Superseded | SUPERSEDED by PX4 EKF2 wheel-encoder fusion (firmware), validated 2026-06-12 (log_150). ROS2 robot_localization node not pursued.
Phase 4 | Sensor Fusion | Encoder Bridge | Superseded | SUPERSEDED — RoboClaw encoder counts feed PX4 EKF2 directly; no STM32→/wheel_odom bridge needed.
Phase 2 | Diagnostics | /rpp/debug Float32MultiArray | Live | 47-field array: xtrack, heading_err, L_d, speed, κ, dist_to_goal, pose_age, state_code, preview_κ, yaw_rate_cmd, all params snapshot, spray_active
Phase 2 | Diagnostics | rosbag Capture | Live | Record /rpp/debug, /mavros/local_position/pose, /mavros/state for post-flight analysis
Phase 2 | Diagnostics | xtrack_logger CSV Export | Live | Per-tick xtrack + curvature to CSV for offline scatter/histogram analysis
Phase 2 | Diagnostics | capture_telemetry.py Tool | Live | WebSocket sniff tool: NDJSON output, configurable sample count, field filtering
Phase 2 | Live Tuning | RPP Param API | Live | Get/set all 36+ RPP params at runtime via /api/rpp/params — no node restart required
Phase 2 | Live Tuning | PX4 Param API | Live | Read/write PX4 FCU params via MAVROS bridge — /api/params/{name}
Phase 2 | Sensor Fusion | EKF2 Wheel-Encoder Fusion | Validated | RoboClaw encoder counts → PX4 EKF2 body-velocity fusion. RBCLW_COUNTS_REV=148000, EKF2_WENC_CTRL=1; validated log_150 (motion scale 1.056, standstill drift 0.3cm/7s).
Baseline | Process | Trusted companion pin (colinear-fix) | Live | 2026-07-11: test/colinear-fix @ 3b7841a = cd44884 controller + OFFBOARD_POSITION_MODE_PLAN.md. Segment/stop-pivot production; collinear PRE/MARK/AFT momentum preserved.

## Parameters
All Parameters | RPP controller, spray node, server config, and path engine tunable values
System | Group | Parameter | Type | Default Value | Min | Max | Unit | Description
RPP Controller | Velocity | max_linear_vel | float | 0.8 | 0.0 | 3.0 | m/s | Hardware velocity ceiling — absolute maximum forward speed
RPP Controller | Velocity | min_linear_vel | float | 0.15 | 0.0 | 1.0 | m/s | Velocity floor for MARK segments to prevent stall
RPP Controller | Velocity | mission_speed | float | 0.35 | 0.0 | 2.0 | m/s | Operator speed knob — single speed applied to the entire mission
RPP Controller | Velocity | regulated_linear_scaling_min_speed | float | 0.3 | 0.0 | 2.0 | m/s | Floor for lateral-accel regulated speed (P4.1)
RPP Controller | Velocity | max_linear_accel | float | 0.35 | 0.0 | 5.0 | m/s² | Acceleration ramp limit (0 = off)
RPP Controller | Velocity | max_linear_decel | float | 0.5 | 0.0 | 5.0 | m/s² | Deceleration limit used to derive braking distance
RPP Controller | Lookahead | min_lookahead_dist | float | 0.52 | 0.1 | 5.0 | m | Minimum lookahead distance for tight tracking
RPP Controller | Lookahead | max_lookahead_dist | float | 1.0 | 0.1 | 10.0 | m | Maximum lookahead distance for smooth long-range recovery
RPP Controller | Lookahead | lookahead_time | float | 1.6 | 0.1 | 10.0 | s | Closed-loop L_d scaling: L_d = lookahead_time × speed
RPP Controller | Curvature Reg | a_lat_max | float | 0.3 | 0.05 | 2.0 | m/s² | Lateral accel limit: v ≤ sqrt(a_lat_max / ¦κ¦) on curves (P4.1)
RPP Controller | Goal Handling | xy_goal_tolerance | float | 0.02 | 0.005 | 1.0 | m | DONE gate threshold — distance to final waypoint
RPP Controller | Goal Handling | min_goal_travel_m | float | 0.5 | 0.0 | 10.0 | m | Require this travel before DONE gate is armed
RPP Controller | Goal Handling | approach_velocity_scaling_dist | float | 0.6 | 0.0 | 5.0 | m | Distance at which speed begins ramping down toward goal
RPP Controller | Goal Handling | min_approach_linear_velocity | float | 0.1 | 0.0 | 1.0 | m/s | Minimum speed in the goal approach zone
RPP Controller | Goal Handling | p4_zero_vel_threshold | float | 0.02 | 0.0 | 0.5 | m/s | Snap ¦v¦ < X to zero to avoid creep
RPP Controller | Safety | pose_max_age_s | float | 0.5 | 0.05 | 5.0 | s | Stale pose threshold — RPP halts if exceeded
RPP Controller | Safety | ekf_jump_threshold_m | float | 0.05 | 0.01 | 1.0 | m | Position jump rejection threshold (P0.2)
RPP Controller | Safety | require_rtk_fix | bool | True | — | — | — | Gate non-zero velocity on RTK fix_type=6 (P0.3)
RPP Controller | Safety | path_frame_id | string | local_ned | — | — | — | Expected frame_id in incoming nav_msgs/Path
RPP Controller | Predictive κ (P1.1) | preview_curvature_n | int | 4 | 1 | 20 | pts | Number of lookahead points for worst-κ preview
RPP Controller | Adaptive L_d (P1.2) | xtrack_lookahead_gain | float | 0.05 | 0.0 | 5.0 | m/m | Cross-track error gain added to L_d
RPP Controller | Path Conditioning (P1.3) | path_resample_spacing_m | float | 0.08 | 0.0 | 1.0 | m | Uniform resample spacing (0 = off)
RPP Controller | Path Conditioning (P1.3) | corner_smooth_radius_m | float | 0.5 | 0.0 | 5.0 | m | Inscribed arc radius at hard corners (0 = off)
RPP Controller | Path Conditioning (P1.3) | corner_smooth_arc_pts | int | 6 | 3 | 50 | pts | Number of points per smoothed arc
RPP Controller | Tracking Profile | tracking_profile | string | auto | — | — | — | Profile: auto ¦ segment ¦ smooth
RPP Controller | Tracking Profile | segment_corner_threshold_deg | float | 45.0 | 1.0 | 180.0 | deg | Auto-profile corner angle threshold for segment vs smooth
RPP Controller | Tracking Profile | segment_slowdown_dist | float | 0.50 | 0.0 | 5.0 | m | Distance before corner to start decelerating (segment profile)
RPP Controller | Tracking Profile | segment_min_corner_speed | float | 0.08 | 0.0 | 1.0 | m/s | Minimum forward speed at corner apex (segment profile)
RPP Controller | Tracking Profile | segment_corner_acceptance_radius | float | 0.05 | 0.005 | 1.0 | m | Distance from corner vertex to start pivot alignment
RPP Controller | Tracking Profile | segment_heading_tolerance_deg | float | 2 | 0.1 | 45.0 | deg | Max heading error before advancing past corner [as-flown log_183/square=2.0]
RPP Controller | Tracking Profile | segment_yaw_rate_gain | float | 1.5 | 0.0 | 10.0 | rad/s per rad | Proportional yaw rate gain during corner pivot
RPP Controller | Tracking Profile | segment_stop_yaw_rate_threshold | float | 0.05 | 0 | 1 | rad/s | CORNER_STOP yaw-rate floor — rover must rotate <this (with speed floor) for dwell before pivot (BUG-T1 036f116)
RPP Controller | Tracking Profile | segment_align_settle_s | float | 0.20 | 0 | 2 | s | CORNER_ALIGN dwell: heading+yaw-rate must both be stable this long before exit→TRACK (BUG-T1 036f116)
RPP Controller | Latency (P2.4) | use_imu_extrapolation | bool | False | — | — | — | Enable velocity-based pose extrapolation
RPP Controller | Latency (P2.4) | imu_max_extrap_age_s | float | 0.10 | 0.0 | 1.0 | s | Maximum extrapolation duration beyond pose_max_age
RPP Controller | Feedforward YR (P3.1) | use_feedforward_yaw_rate | bool | True | — | — | — | Enable ω = κ·v + k_ψ·θ_e yaw rate output
RPP Controller | Feedforward YR (P3.1) | yaw_rate_feedback_gain | float | 0.0 | 0.0 | 10.0 | rad/s/rad | Heading error feedback term k_ψ
RPP Controller | Feedforward YR (P3.1) | max_yaw_rate_body | float | 0.45 | 0.0 | 5.0 | rad/s | Body yaw rate clamp (≈57°/s at 1.0)
Spray Controller | Actuator | actuator_set_index | int | 1 | 1 | 6 | — | Which Actuator Set param carries ON/OFF signal
Spray Controller | Actuator | on_value | float | 1.0 | — | — | — | +1.0 → MAX PWM → solenoid ON
Spray Controller | Actuator | off_value | float | -1.0 | — | — | — | -1.0 → MIN PWM → solenoid OFF
Spray Controller | Safety | debounce_samples | int | 3 | — | — | samples | ≈60ms at 50Hz — prevent chatter on rapid transitions
Spray Controller | Safety | reassert_hz | float | 2.0 | — | — | Hz | Re-send desired spray state to compensate dropped commands
Spray Controller | Safety | require_offboard | bool | True | — | — | — | Only spray when FCU mode = OFFBOARD
Spray Controller | Safety | active_timeout_s | float | 0.5 | — | — | s | Force OFF if /spray/active goes stale beyond this
Spray Controller | Safety | manual_override_timeout_s | float | 10.0 | — | — | s | Hard expiry on manual bench-test ON command
Server Config | Telemetry | TELEMETRY_HZ | int | 10 | — | — | Hz | WebSocket telemetry push rate
Server Config | Safety | POSE_STALE_MS | int | 500 | — | — | ms | Pose staleness threshold for server-side watchdog
Server Config | Safety | SAFETY_STALE_GRACE_S | float | 1.0 | — | — | s | Abort after sustained stale beyond this grace period
Server Config | Mission | DONE_SETTLE_S | float | 1.0 | — | — | s | Require 1s in DONE state before declaring mission complete
Server Config | Spray | SPRAY_LITERS_PER_METER | float | 0.012 | — | — | L/m | Marking fluid consumption rate (env-tunable)
Server Config | Spray | MAX_SPRAY_TEST_DURATION_S | int | 10 | — | — | s | Max duration for manual spray bench test
Server Config | Planning | RMSE_MAX | float | 0.05 | — | — | m | DXF→NED alignment RMSE quality gate
Server Config | Planning | STAGING_TTL_S | int | 3600 | — | — | s | Staged mission lifetime before expiry
Path Engine | Discretization | line_spacing | float | 0.05 | — | — | m | MARK segment waypoint spacing
Path Engine | Discretization | transit_spacing | float | 0.15 | — | — | m | TRANSIT segment waypoint spacing
Path Engine | Velocity | marking_speed | float | 0.35 | — | — | m/s | Speed during MARK segments
Path Engine | Velocity | transit_speed | float | 0.5 | — | — | m/s | Speed during TRANSIT repositioning segments
Path Engine | Extensions | enable_path_extensions | bool | True | — | — | — | Enable pre/aft spray lead-in/out extension
Path Engine | Extensions | pre_extension_m | float | 0.035 | — | — | m | Lead-in distance before MARK segment starts
Path Engine | Extensions | aft_extension_m | float | 0.0035 | — | — | m | Lead-out distance after MARK segment ends
RPP Controller | Tracking Profile | segment_brake_velocity_cap_m_s | float | 0.08 | 0.0 | 0.2 | m/s | Max reverse longitudinal velocity for active CORNER_STOP braking; 0 disables. Baseline pin 2026-07-11 (cd44884).

## Pending Tasks
Open tasks as of 2026-07-11 ¦ TRUSTED BASELINE: test/colinear-fix @ 3b7841a (controller=cd44884). July mainline stop/hold experiments out of tree. | Baseline pin 2026-07-11 — continue Phase 3 path/CRS/spray/pipeline from this branch | Total includes BASE-T1 pin + SPD-T1 backlog; BUG-T1/T2/T3 Done
Sprint / Phase | Task ID | Priority | Status | Title | Description | Blocker / Notes
Sprint 1 — Corner xtrack | S1-T1 | HIGH | Done | Deploy & verify current RPP on Jetson | git pull, restart rpp-pipeline, verify /rpp/debug array size=39, confirm yaw-rate path type_mask | DONE 06-12. Deployed; /rpp/debug now 47-field (was 39).
Sprint 1 — Corner xtrack | S1-T2 | HIGH | Done | Capture baseline corner bag | Run square_2x2 with current params, record /rpp/debug + /mavros/local_position/pose | DONE. Bags captured 06-08/06-09/06-12 (arc + square_cornerfix).
Sprint 1 — Corner xtrack | S1-T3 | HIGH | Superseded | Sweep yaw_rate_feedback_gain | Test k_ψ = 0.0, 0.3, 0.6; record peak ¦xtrack¦ per value on square_2x2 | CLOSED — NO-OP. In velocity OFFBOARD mode PX4 DifferentialOffboardMode discards trajectory_setpoint.yawspeed; companion yaw_rate_feedback_gain never reaches the rate loop. Corner goal met via segment stop-pivot instead.
Sprint 1 — Corner xtrack | S1-T4 | HIGH | Closed | Tighten a_lat_max to 0.2 m/s² | Lower from 0.3 → 0.2 m/s² for ~18% speed reduction at corners; cross-check corner_smooth_radius_m | Not needed — corner goal met at a_lat_max=0.3 (frozen). Re-open only on regression.
Sprint 1 — Corner xtrack | S1-T5 | HIGH | Done | Validate corner xtrack ≤5cm | Run tuned square_2x2, extract max ¦debug[0]¦ during TRACKING state; gate: ≤5cm peak | MET ~2cm. square_cornerfix_20260612_201142: RPP xtrack 0.52cm RMS/1.45cm max; geometric 0.82cm RMS/2.17cm max (corner cusp). 1 run — repeatability pending VAL-T1.
Sprint 1 — Corner xtrack | S1-T6 | MEDIUM | N/A | Corner smoothing audit | If S1-T5 fails: increase corner_smooth_arc_pts, verify resample spacing, re-run validation | Gate passed; smoothing audit not required.
Sprint 2 — Sensor Fusion | S2-T7 | MEDIUM | Superseded | Build robot_localization node | Create localization_node.py + robot_localization.yaml EKF config; add /odom subscriber to RPP controller | Encoder fusion delivered by PX4 EKF2 wheel-encoder fusion (firmware), VALIDATED log_150. robot_localization ROS2 node NOT needed.
Sprint 2 — Sensor Fusion | S2-T8 | MEDIUM | Superseded | Wire encoder bridge | STM32 → /wheel_odom ROS2 topic — hardware wiring and firmware driver | No STM32 bridge — RoboClaw encoder counts feed PX4 EKF2 directly (RBCLW_COUNTS_REV). Superseded by EKF2 path.
Sprint 2 — Sensor Fusion | S2-T9 | MEDIUM | Done | Deploy & test fused localization | Enable use_fused_odom param, validate xtrack ≤3cm as prerequisite for Sprint 2 | DONE via EKF2 — log_150: motion scale 1.056, standstill drift 0.3cm/7s. NOTE: confirm live FCU has EKF2_WENC_CTRL=1 + RBCLW_COUNTS_REV=148000 (12-06 snapshot still shows 0/1200).
Phase 3 — Spray | P3-T1 | HIGH | Pending | QGC AUX config | Set AUX output function=301, configure MIN/MAX/DISARMED/FAILSAFE PWM in QGroundControl | QGC on Mac — must be done at hardware
Phase 3 — Spray | P3-T2 | HIGH | Pending | Hardware wiring | Wire solenoid relay/MOSFET to AUX output; flyback diode; isolated 12V supply | Requires physical hardware access
Phase 3 — Spray | P3-T3 | HIGH | Done | Propagate spray flags → /path z-channel | Extend publish_path() to write spray_flags into pose.position.z per waypoint | DONE — z-channel transport live: server/ros_node.py:807 + path_publisher_node.py:521 write pose.z; RPP reads at :555.
Phase 3 — Spray | P3-T4 | CRITICAL | Done | Flag propagation through path conditioning | Extend _smooth_corners() + _resample_path() to carry parallel flag lists; AND rule at boundaries; unit tests CRITICAL | DONE (CRITICAL) — _smooth_corners/_resample_path/_simplify_path_for_profile carry parallel flags, AND-rule at boundaries (:831,:849). Tested: test_spray_flag_conditioning.py.
Phase 3 — Spray | P3-T5 | HIGH | Done | Add spray_controller to launch file | Add spray_controller_node to rpp_pipeline.launch.py and rpp_start.sh | DONE — wired in BOTH rpp_pipeline.launch.py (spray_proc) and prod launcher rpp_start.sh (start_node spray_controller).
Phase 3 — Spray | P3-T6 | MEDIUM | Done | Server marking_state integration | Verify TelemetryData.marking_state (off/transit/marking) populated from /spray/state; WebSocket push | DONE — marking_state in models.py:89 + main.py:306 + routes/telemetry.py (marking/transit/off), Socket.IO push.
Phase 3 — Spray | P3-T7 | MEDIUM | Pending | Frontend marking state pill | Show marking_state indicator in mobile frontend (green=marking, grey=transit, off=stopped) | Depends on P3-T6
Phase 3 — Spray | P3-T8 | MEDIUM | Pending | Latency measurement on bench | Measure end-to-end ON/OFF latency (solenoid LED + log timestamp); feed into path_engine.spray compensation params | Requires bench + solenoid wired
Phase 3 — Spray | P3-T9 | HIGH | Done | Integration tests — spray flag propagation | SITL: verify flag propagation through conditioning, disarm→OFF, E-stop→OFF, staleness watchdog→OFF | DONE (offline) — test_spray_flag_conditioning.py (propagation/AND-rule) + test_spray_manual_override.py (disarm/staleness→OFF). On-HW SITL folds into P3-T11.
Phase 3 — Spray | P3-T10 | HIGH | Done | Unit tests — spray controller | Edge-detect, debounce, fail-safes, flag carry-through unit tests for spray_controller_node.py | DONE — test_spray_manual_override.py: 9 tests (debounce, edge, disarm/not-OFFBOARD reject, watchdog expiry, staleness scoping, disarm-failsafe precedence, shutdown→OFF).
Phase 3 — Spray | P3-T11 | HIGH | Pending | Safety validation before field use | Verify all spray fail-safes on hardware: disarm→OFF, E-stop→OFF, MANUAL mode→OFF, solenoid flyback | Block field use until done
Phase 3 — Spray | P3-T12 | MEDIUM | Pending | Bench test DO_SET_ACTUATOR manually | Confirm MAVLink cmd 187 fires actuator via QGC actuator testing before full integration | Pre-req for all spray tasks
Infra | I-T1 | LOW | Superseded | robot_localization.yaml deployment | Activate EKF fusion config (config/robot_localization.yaml) once encoder bridge wired | robot_localization.yaml not needed — EKF2 firmware fusion is the production path.
Infra | I-T2 | LOW | Pending | Review rpp-pipeline launch vs rpp_start.sh | Launch file is dead code — verify all nodes listed in rpp_start.sh; remove or update launch file to avoid confusion | Low risk — cosmetic
Infra | I-T3 | MEDIUM | Pending | Field test tracking profiles | tracking_profile=auto bench-verified; needs first field run with real DXF mission to validate entity-level profile switching | Requires field access
Infra | I-T4 | LOW | Pending | xtrack_logger_node CSV path config | Make log_file param configurable in systemd env file; currently defaults may fill Jetson disk on long runs | Low urgency
Validation | VAL-T1 | HIGH | Pending | Repeatability validation — 9 bags | Analyse 3×arc + 3×square + 3×lshape (delivered 06-13). Per-shape RMS/max/p95 mean AND run-to-run spread; flag aborted/no-/path runs; update confidence per shape in CLAUDE.md + PROGRESS.md. | Bags arrive tomorrow. Confidence currently single-run for square.
Phase 3 — Path | PE-T1 | HIGH | Active | Path engine + trajectory planning | Mission/path generation hardening: per-entity segment splitting, corner handling, resample/smooth robustness, transit insertion. Now primary focus (controller closed). | Active focus #1. ¦ Continue from test/colinear-fix @ 3b7841a (2026-07-11).
Phase 3 — Path | PE-T2 | HIGH | Active | CRS / coordinate handling | Coordinate reference system + geodesic conversion for path import (DXF/QGC → local NED). Validate least-squares alignment RMSE ≤0.05m end-to-end. | Active focus #2. Ties to DXF→NED alignment feature.
Phase 3 — Pipeline | PE-T3 | HIGH | Pending | Full-pipeline validation | End-to-end on hardware: CAD/DXF → path → mission → drive → spray. Confirms controller + path engine + spray together. | Active focus #4. Depends on spray P3-T* + PE-T1/T2.
Bug — Controller | BUG-T1 | HIGH | Done | Stop-pivot corner oscillation / jerk | At segment stop-and-pivot corners the rover oscillates/jerks during STOP→ALIGN→resume. Analyse a corner/square ros bag + segment FSM (CORNER_STOP/CORNER_ALIGN), pivot yaw control (segment_yaw_rate_gain=1.5, RO_YAW_RATE_P=0.17/I=0.01, RO_YAW_RATE_LIM=30), and decel overshoot near zero speed. Fix to a clean single pivot. | DONE — VALIDATED square_2x2_20260615_144019: pivots are clean single-direction spins, only 1 significant yaw-rate reversal (>0.1) / 0 large (>0.2) across 3 corners (was 8/2 on 06-13). xtrack 0.53cm RMS/2.22cm max. Oscillation eliminated. Minor: pivots ~6s (near 5s watchdog), 2/3 exit ~0.17 rad/s residual — optional refinement.
Bug — Path/Controller | BUG-T2 | HIGH | Done | U-turn (line+tangent arc) not continuous — stop&go | Tangent U-turn = line(1m)→arc(R0.5m / 2m dia)→line. Tangent junctions are C1-continuous (no heading jump) so motion SHOULD be smooth/continuous. Actual: tracks line, STOPS at junction, pivots/aligns, tracks arc, STOPS, resumes line. Analyse path-engine profile splitting (auto: per-entity run split + pivot-align at transitions) and RPP segment/smooth FSM; allow continuous flow across tangent (≈0°) junctions, stop-pivot ONLY at hard corners. Validate on the U-turn bag. | DONE — VALIDATED 13-06 U-turn bags: continuous flow through line→tangent-arc→line, 0 bad stops, 0.97cm RMS. Commit 1af51ac.
Bug — Heading/Sign | BUG-T3 | CRITICAL | Done | Wrong initial turn direction — turns away, drives reverse | Rover heading West, first segment line toward North. Expected: turn right/CW ~90° to North, drive forward. Actual: turns SOUTH (wrong way) and navigates in REVERSE to reach North. Analyse heading/yaw sign + shortest-angle wrap in controller (ENU↔NED yaw_NED=pi/2-yaw_ENU; bearing=atan2(vE,vN)), spot-turn direction (RD_TRANS_DRV_TRN), and signed-speed/reverse projection (PX4 negative-speed = 'turn 180 & drive'). Fix wrong-direction + reverse navigation. Reproduce with a bag where start heading opposes the first segment. | DONE 2026-06-13 (opus) commit 510be9b — forward-cone clamp on first-segment velocity. Deployed: FF pull, rpp-pipeline restart (2s, MAVROS intact), 3/3 services active, API ping OK. Mac==origin==Jetson.
Phase 3 — Path | PE-T4 | HIGH | Pending | Validate path-engine Extensions + transit | End-to-end test of enable_path_extensions (pre_extension_m=0.035 / aft_extension_m=0.0035 spray lead-in/out) and that TRANSIT segments (transit_speed=0.5, transit_spacing=0.15) connect MARK segments correctly. Confirm extension points inserted with the right spray flags and geometry. Once extensions + transit validated → path-engine extension feature COMPLETE. | Priority #4. Ties to PE-T1/PE-T2. Verify on a real DXF mission + bag.
Phase 3 — Spray | PE-T5 | HIGH | Pending | Verify transit/mark state transitions (segment vs smooth) | Verify marking_state / /spray/active flips correctly at segment boundaries — MARK on mark segments, TRANSIT on repositioning — and behaves correctly under BOTH tracking profiles (segment stop-pivot AND smooth). Cross-check /spray/active + marking_state telemetry against path z-channel flags on a bag; confirm no missed/late transitions at corners or profile switches. | Priority #5. Spray SW + flag-conditioning already built (P3-T4 done); this validates the live state machine per profile.
Future — Speed | SPD-T1 | MEDIUM | Backlog | High-speed tuning: 1 m/s line / 0.6 m/s arc | Currently validated at 0.35 m/s. Raise to 1.0 line / 0.6 arc. KEY ITEMS: (1) PREREQ verify top speed — RO_MAX_THR_SPEED=0.9 ⇒ full throttle ≈0.9-0.95 m/s, so 1.0 has NO control headroom; confirm RoboClaw QPPS/gearing allows ≥1.1 m/s first. (2) Raise caps: max_linear_vel 0.8→≥1.1, RO_SPEED_LIM 0.30→≥1.1. (3) Line/arc split is FREE via a_lat regulator: set mission_speed=1.0, a_lat_max≈0.24 → straights 1.0, R1.5 arc auto ~0.6 (v=sqrt(a_lat/κ)); tighter circles auto-slow. (4) Tighten speed loop RO_SPEED_P 0.18→~0.4-0.6 / RO_SPEED_I 0.02→~0.1 (already overshoots 20% at 0.35). (5) Corner braking: stop dist=v²/2·RO_DECEL=0.5/0.6≈0.83m > segment_slowdown_dist=0.5 → scale slowdown_dist with speed (≥1.0m) or raise RO_DECEL_LIM, else corner overshoot. (6) Arc heading lag worsens: ω=v/R bigger → following err ω/RO_YAW_P (0.6 on R1.5 → ~15° at RO_YAW_P=1.5); raise RO_YAW_P or go body_rate offboard, else arc xtrack grows. (7) Check max_yaw_rate_body=0.45 vs ω=v/R on tightest circle. (8) Enable use_imu_extrapolation (pose lag 2-5cm at 1 m/s). | Future. Re-validate xtrack budget at speed (RTK/EKF latency dominates more). Do after path/CRS/spray.
Baseline — 2026-07-11 | BASE-T1 | CRITICAL | Done | Pin trusted companion baseline (colinear-fix branch) | Operator-confirmed trustworthy tree: branch test/colinear-fix @ 3b7841a (RPP identical to cd44884). Frozen corner knobs: segment_slowdown_dist=0.50, segment_brake_velocity_cap_m_s=0.08, PRE_CORNER floor=segment_min_corner_speed=0.08, segment_align_settle_s=0.20. Absent: corner_stop_hold_s, completion latch, twist hold_yaw_in_corner_stop. All new work branches from this pin. | Pinned 2026-07-11. Memory: baseline_colinear_fix_2026_07_11. Do not re-merge July param doublings without A/B bags.

## PX4 FCU Params
PX4 FCU Parameters — as-flown 2026-06-12 (log_183). Do NOT push from Jetson; QGC on Mac is source of truth.
Group | PX4 Param | As-flown value | Unit | Notes / source: log_183 (2026-06-12 20:00), QGC = source of truth
Yaw attitude | RO_YAW_P | 1.5 |  | Attitude P. Raised 1.0→1.5 → arc heading lag ~12°→~9°
Yaw rate | RO_YAW_RATE_P | 0.17 |  | Rate-loop P
Yaw rate | RO_YAW_RATE_I | 0.01 |  | Rate-loop I (low)
Yaw rate | RO_YAW_RATE_LIM | 30 | deg/s | 30 — VALIDATED 2026-06-12 (operator fix today): xtrack <2cm. Was 90.
Yaw rate | RO_YAW_ACCEL_LIM | 25 | deg/s² | Yaw accel slew
Yaw rate | RO_YAW_DECEL_LIM | 34 | deg/s² | Yaw decel slew
Speed | RO_SPEED_P | 0.18 |  | Soft — speed overshoots ~0.42 vs 0.35
Speed | RO_SPEED_I | 0.02 |  | Soft
Speed | RO_SPEED_LIM | 0.3 | m/s | Speed cap
Speed | RO_MAX_THR_SPEED | 0.9 | m/s | Speed at full throttle (FF scale)
Speed | RO_ACCEL_LIM | 0.2 | m/s²
Speed | RO_DECEL_LIM | 0.3 | m/s²
Speed | RO_JERK_LIM | 0.3 | m/s³
Diff drive | RD_MAX_THR_YAW_R | 0.95 |  | Max throttle to yaw (cap; only 8% used)
Diff drive | RD_WHEEL_TRACK | 0.47 | m | Wheel track
Diff drive | RD_TANK_MODE | 0 |  | 0 = OFFBOARD-safe
Diff drive | RD_TRANS_DRV_TRN | 0.7 | rad | Drive→spot-turn threshold (~40°)
Diff drive | RD_TRANS_TRN_DRV | 0.03491 | rad | Turn→drive resume (~2°); was 5°
Encoder fusion | EKF2_WENC_CTRL | 1 |  | 1 = ON (validated)
Encoder fusion | EKF2_WENC_RAD | 0.1524 | m | Rolling radius
Encoder fusion | EKF2_WENC_NOISE | 0.1 |  | Meas noise
Encoder fusion | EKF2_WENC_GATE | 3 |  | Innovation gate
Encoder fusion | EKF2_WENC_DELAY | 5 | ms
RoboClaw | RBCLW_COUNTS_REV | 148000 | counts | 148000 = CPR×gear (validated log_150)
RoboClaw | RBCLW_QPPS_MAX | 182655 | counts/s | Autotuned max
RoboClaw | RBCLW_MAX1 | 255 |  | Creep fix
RoboClaw | RBCLW_MAX2 | 255 |  | Creep fix
Safety | COM_OF_LOSS_T | 30 | s | 30 = DEBUG/TEST value (operator). PRODUCTION = 0.3 s — set before field runs.
Safety | COM_OBL_RC_ACT | 5 |  | OFFBOARD-loss action
Safety | COM_RCL_EXCEPT | 4 |  | RC-loss exception
GPS/EKF | EKF2_REQ_GPS_H | 1 | s | Rover-short GPS health window
GPS/EKF | EKF2_GPS_CHECK | 927 | bitmask | 927 — operator-set, VALIDATED. Supersedes earlier 831.
Alloc | CA_R_REV | 3 |  | Bidirectional PWM reversal